## 2023-03-21T11_43_23 616Z_nbH
User ID | Username | Task Count | Space ID | Space Name | Folder ID | Folder Name | List ID | List Name | Parent Task ID | Task ID | Task Name | Task Status | Date Closed | Date Closed Text | Due Date | Due Date Text | Start Date | Start Date Text | Lead Time | Lead Time Text | Time Estimated | Time Estimated Text | Time Spent | Time Spent Text | Tags | Checklists | Date Created | Date Created Text
43093983 | Tayhana Rangel | 1 | 90070175992 | Projetos | 90070557215 | PROJ-DOC-2022-01 - DocManage | 900700969989 | Gerencial | null | 864e3u4p5 | Definição de requisitos | complete | 1677887456490 | 3/3/2023, 8:50:56 PM GMT-3 | 1682665200000 | 4/28/2023, 4:00:00 AM GMT-3 | 1681801200000 | 4/18/2023, 4:00:00 AM GMT-3 | 16009412 | 4 h 27 m |  |  |  |  | [] | {} | 1677871447078 | 3/3/2023, 4:24:07 PM GMT-3
| Unassigned | 5 | 90070175992 | Projetos | 90070557215 | PROJ-DOC-2022-01 - DocManage | 900700935625 | Tarefas | null | 864e3vvq2 | Criação e configuração do banco de dados | Closed | 1677966618533 | 3/4/2023, 6:50:18 PM GMT-3 | 1683270000000 | 5/5/2023, 4:00:00 AM GMT-3 | 1683270000000 | 5/5/2023, 4:00:00 AM GMT-3 | 77437440 | 21 h 31 m | 21600000 | 6 h | 7200000 | 2 h | ["backend","fullstack","teste"] | {} | 1677889181093 | 3/3/2023, 9:19:41 PM GMT-3
| Unassigned | 5 | 90070175992 | Projetos | 90070557215 | PROJ-DOC-2022-01 - DocManage | 900700935625 | Tarefas | null | 864e3vvn0 | Desenvolvimento do modelo de dados | Closed | 1677890033577 | 3/3/2023, 9:33:53 PM GMT-3 | 1683183600000 | 5/4/2023, 4:00:00 AM GMT-3 | 1682924400000 | 5/1/2023, 4:00:00 AM GMT-3 | 869093 | 14 m | 57600000 | 16 h | 43200000 | 12 h | ["backend","fullstack","teste"] | {} | 1677889164484 | 3/3/2023, 9:19:24 PM GMT-3
| Unassigned | 5 | 90070175992 | Projetos | 90070557215 | PROJ-DOC-2022-01 - DocManage | 900700935625 | Tarefas | null | 864e3u660 | Elaboração do documento de requisitos | Closed | 1677877469318 | 3/3/2023, 6:04:29 PM GMT-3 | 1682492400000 | 4/26/2023, 4:00:00 AM GMT-3 | 1681887600000 | 4/19/2023, 4:00:00 AM GMT-3 | 5729294 | 1 h 35 m | 115200000 | 32 h | 108000000 | 30 h | ["requisitos"] | {} | 1677871740024 | 3/3/2023, 4:29:00 PM GMT-3
| Unassigned | 5 | 90070175992 | Projetos | 90070557215 | PROJ-DOC-2022-01 - DocManage | 900700935625 | Tarefas | null | 864e3vvt3 | Criação e configuração de repositório | Closed | 1677966868028 | 3/4/2023, 6:54:28 PM GMT-3 | 1683615600000 | 5/9/2023, 4:00:00 AM GMT-3 | 1683529200000 | 5/8/2023, 4:00:00 AM GMT-3 | 77669050 | 21 h 34 m | 21600000 | 6 h | 14400000 | 4 h | ["backend","fullstack"] | {} | 1677889198978 | 3/3/2023, 9:19:58 PM GMT-3
| Unassigned | 5 | 90070175992 | Projetos | 90070557215 | PROJ-DOC-2022-01 - DocManage | 900700935625 | Tarefas | null | 864e3ymng | Elaboração de identidade visual | Closed | 1677969358642 | 3/4/2023, 7:35:58 PM GMT-3 | 1683270000000 | 5/5/2023, 4:00:00 AM GMT-3 | 1682924400000 | 5/1/2023, 4:00:00 AM GMT-3 | 832269 | 14 m | 86400000 | 24 h | 86400000 | 24 h | ["frontend","teste"] | {} | 1677968526373 | 3/4/2023, 7:22:06 PM GMT-3

## Clickup
Space ID | Space Name | Folder ID | Folder Name | List ID | List Name | id servico | Task ID | Task Name | Task Status | Date Closed | Time Spent | Date Created | Date In Progress | Date Blocked | Date Completed | Date Review | Date Accepted | Date Deploy Prod
90070175992 | Projetos | 90070557215 | PROJ-DOC-2022-01 - DocManage | 900700935625 | Tarefas | Implementação | 864e3u660 | Elaboração do documento de requisitos | Closed | 2023-04-21 | 108000000 | 2023-04-19 | 2023-04-19 | 2023-04-21 | 2023-04-21 | 2023-04-21 | 2023-04-21 | 2023-04-21
90070175992 | Projetos | 90070557215 | PROJ-DOC-2022-01 - DocManage | 900700935625 | Tarefas | Implementação | 864e3vvq2 | Criação e configuração do banco de dados | Closed | 2023-05-05 | 7200000 | 2023-05-01 | 2023-05-05 |  | 2023-05-05 | 2023-05-05 | 2023-05-05 | 2023-05-05
90070175992 | Projetos | 90070557215 | PROJ-DOC-2022-01 - DocManage | 900700935625 | Tarefas | Implementação | 864e3vvn0 | Desenvolvimento do modelo de dados | Closed | 2023-05-03 | 43200000 | 2023-05-01 | 2023-05-01 |  | 2023-05-02 | 2023-05-03 | 2023-05-03 | 2023-05-03
90070175992 | Projetos | 90070557215 | PROJ-DOC-2022-01 - DocManage | 900700935625 | Tarefas | Implementação | 864e3vvt3 | Criação e configuração de repositório | Closed | 2023-05-08 | 14400000 | 2023-05-01 | 2023-05-08 |  | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-05-08
90070175992 | Projetos | 90070557215 | PROJ-DOC-2022-01 - DocManage | 900700935625 | Tarefas | Implementação | 864e3ymng | Elaboração de identidade visual | Closed | 2023-05-05 | 86400000 | 2023-05-01 | 2023-05-01 |  | 2023-05-04 | 2023-05-05 | 2023-05-05 | 2023-05-05
90070175992 | Projetos | 90070557215 | PROJ-DOC-2022-01 - DocManage | 900700935625 | Tarefas | Implementação | 864e3ymnu | Protótipos | In Progress |  |  | 2023-05-01 | 2023-05-05
90070175992 | Projetos | 90070557215 | PROJ-DOC-2022-01 - DocManage | 900700935625 | Tarefas | Implementação | 864e3vvvj | Preparação do ambiente de homologação e produção | Open |  |  | 2023-05-01
90070175992 | Projetos | 90070557215 | PROJ-DOC-2022-01 - DocManage | 900700935625 | Tarefas | Implementação | 864e3ymp1 | Desenvolvimento da interface do usuários | Open |  |  | 2023-05-01

## Board
id | data fato | Data | Space ID | id projeto | Work In Progress | Open | In Progress | Blocked | Completed | Review | Accepted | Deploy Prod | Closed
1 | 2023-04-19 | 20230419 | 90070175992 | 90070557215 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2023-04-21 | 20230421 | 90070175992 | 90070557215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
3 | 2023-05-01 | 20230501 | 90070175992 | 90070557215 | 2 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 1
4 | 2023-05-02 | 20230502 | 90070175992 | 90070557215 | 2 | 5 | 1 | 0 | 1 | 0 | 0 | 0 | 1
5 | 2023-05-03 | 20230503 | 90070175992 | 90070557215 | 1 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 2
6 | 2023-05-04 | 20230504 | 90070175992 | 90070557215 | 1 | 5 | 0 | 0 | 1 | 0 | 0 | 0 | 2
7 | 2023-05-05 | 20230505 | 90070175992 | 90070557215 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 4
8 | 2023-05-08 | 20230508 | 90070175992 | 90070557215 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 5

## Manutenção
id | data fato | ID Cliente | id projeto | data | tempo manutenção
1 | 2023-04-14 | 482 | 90070557215 | 20230414 | 960